## timelog (1)
Date | User | Project | Category | Activity | Payment Performed Class | Issue | Comment | Hours | MPS
4617100% | Clara Bécares Rodríguez | Natura2000 | Testing | Development | extra-muros | Task #303483: Testing activitites |  | 7 | 1.1.16
4617100% | Clara Bécares Rodríguez | Natura2000 | Analysis | Development | extra-muros | Task #302531: Data model revision and adaptation |  | 3.5 | 1.1.16
4617100% | Isabel Olea | Natura2000 |  | Development | extra-muros | Task #303332 |  | 2 | 1.1.16
4617100% | Natalia Orio Moreno | Natura2000 | Analysis | Development | extra-muros | Task #302531: Data model revision and adaptation | final conclusions to expose in the progress meeting | 3 | 1.1.16
4617000% | Clara Bécares Rodríguez | Natura2000 | Testing | Development | extra-muros | Task #303483: Testing activitites |  | 4 | 1.1.16
4617000% | Isabel Olea | Natura2000 |  | Development | extra-muros | Task #303332 |  | 2 | 1.1.16
4617000% | Natalia Orio Moreno | Natura2000 | Meetings | Development | extra-muros | Task #302497: Biweekly meetings | meeting and notes | 2 | 1.1.16
4617000% | Natalia Orio Moreno | Natura2000 | Analysis | Development | extra-muros | Task #302531: Data model revision and adaptation | design of possible solution - technical document | 3 | 1.1.16
4616900% | Alba Lallana Martín | Natura2000 | Bug fixing | Development | extra-muros | Task #303484: Bug fixing |  | 2 | 1.1.16
4616900% | Clara Bécares Rodríguez | Natura2000 | Testing | Development | extra-muros | Task #303483: Testing activitites |  | 6 | 1.1.16
4616900% | Isabel Olea | Natura2000 |  | Development | extra-muros | Task #303332 |  | 2 | 1.1.16
4616900% | Natalia Orio Moreno | Natura2000 | Meetings | Development | extra-muros | Task #302497: Biweekly meetings |  | 2 | 1.1.16
4616900% | Yolanda Carrasco | Natura2000 | Analysis | Development | extra-muros | Task #302531: Data model revision and adaptation | Clara Support | 1 | 1.1.16
4616800% | Alba Lallana Martín | Natura2000 | Bug fixing | Development | extra-muros | Task #303484: Bug fixing |  | 8.5 | 1.1.16
4616800% | Clara Bécares Rodríguez | Natura2000 | Testing | Development | extra-muros | Task #303483: Testing activitites |  | 6.5 | 1.1.16
4616800% | Isabel Olea | Natura2000 |  | Development | extra-muros | Task #303332 |  | 2 | 1.1.16
4616800% | Natalia Orio Moreno | Natura2000 |  | Development | extra-muros | Task #303332 | review of the complete migration | 4 | 1.1.16
4616700% | Alba Lallana Martín | Natura2000 | Bug fixing | Development | extra-muros | Task #303484: Bug fixing |  | 8.5 | 1.1.16
4616700% | Clara Bécares Rodríguez | Natura2000 | Testing | Development | extra-muros | Task #303483: Testing activitites |  | 5.5 | 1.1.16
4616700% | Esther Ruiz | Natura 2000 backbone |  | Meeting | extra-muros | Task #302389: Meetings with DG-ENV, ETC and EEA | UL meeting | 2 | 1.2.135
4616400% | Alba Lallana Martín | Natura2000 | Bug fixing | Development | extra-muros | Task #303484: Bug fixing |  | 7 | 1.1.16
4616400% | Esther Ruiz | Natura 2000 backbone |  | Development | extra-muros | Task #304183 | Requested to EU-Login IT stuff several times | 2 | 1.2.135
4616400% | Natalia Orio Moreno | Natura2000 | Analysis | Development | extra-muros | Task #302531: Data model revision and adaptation | second round of doubts | 2 | 1.1.16
4616300% | Alba Lallana Martín | Natura2000 |  | Development | extra-muros | Task #302493 |  | 7.5 | 1.1.16
4616300% | Clara Bécares Rodríguez | Natura2000 | Testing | Development | extra-muros | Task #303483: Testing activitites |  | 4.5 | 1.1.16
4616300% | Esther Ruiz | Natura 2000 backbone |  | Meeting | extra-muros | Task #302389: Meetings with DG-ENV, ETC and EEA | UL meeting | 2 | 1.2.135
4616300% | Esther Ruiz | Natura 2000 backbone |  | Development | extra-muros | Task #303832: AD hoc extraction: list of sites where an habitat has been reported more than once | Coordination, comunication | 2 | 1.2.135
4616200% | Alba Lallana Martín | Natura2000 |  | Development | extra-muros | Task #302493 |  | 8.5 | 1.1.16
4616200% | Clara Bécares Rodríguez | Natura2000 | Testing | Development | extra-muros | Task #303483: Testing activitites |  | 3.5 | 1.1.16
4616200% | Esther Ruiz | Natura 2000 backbone |  | Meeting | extra-muros | Task #302389: Meetings with DG-ENV, ETC and EEA | Biweekly meetings: preparation and attendance | 4 | 1.2.135
4616100% | Alba Lallana Martín | Natura2000 |  | Development | extra-muros | Task #302493 |  | 8.5 | 1.1.16
4616100% | Esther Ruiz | Natura 2000 backbone |  | Development | extra-muros | Task #303352: Sites added/deleted by lineage , bioregions and site type | Coordination, comunication | 4 | 1.2.135
4616100% | Esther Ruiz | Natura 2000 backbone |  | Development | extra-muros | Task #303428: Ad-hoc extraction: Generate extraction of the species that are shown several times | Coordination, comunication | 2 | 1.2.135
4616100% | Natalia Orio Moreno | Natura2000 | Analysis | Development | extra-muros | Task #302531: Data model revision and adaptation | review of the technica analysos | 3 | 1.1.16
4616100% | Oscar Esparza García | Natura 2000 backbone |  | Development | extra-muros | Task #303033: Review Lineage and critical changes | review spatial lineage detection | 3 | 1.2.135
4616000% | Alba Lallana Martín | Natura2000 |  | Development | extra-muros | Task #302493 |  | 8.5 | 1.1.16
4615700% | Alba Lallana Martín | Natura2000 |  | Development | extra-muros | Task #302493 |  | 7 | 1.1.16
4615700% | Clara Bécares Rodríguez | Natura2000 | Analysis | Development | extra-muros | Task #302531: Data model revision and adaptation |  | 1 | 1.1.16
4615700% | Josu Olaso | Natura2000 | Testing | Development | extra-muros | Task #303483: Testing activitites |  | 4 | 1.1.16
4615600% | Alba Lallana Martín | Natura2000 |  | Development | extra-muros | Task #302493 |  | 8.5 | 1.1.16
4615600% | Clara Bécares Rodríguez | Natura2000 | Maintenance | Development | extra-muros | Task #302527: Review and removal of deprecated services |  | 2 | 1.1.16
4615600% | Clara Bécares Rodríguez | Natura2000 | Analysis | Development | extra-muros | Task #302531: Data model revision and adaptation |  | 1 | 1.1.16
4615600% | Esther Ruiz | Natura 2000 backbone |  | Development | extra-muros | Task #303352: Sites added/deleted by lineage , bioregions and site type | Coordination, comunication | 4 | 1.2.135
4615600% | Josu Olaso | Natura2000 | Testing | Development | extra-muros | Task #303483: Testing activitites |  | 5.5 | 1.1.16
4615600% | Natalia Orio Moreno | Natura2000 | Analysis | Development | extra-muros | Task #302531: Data model revision and adaptation | list of questions and cases | 2 | 1.1.16
4615500% | Alba Lallana Martín | Natura2000 |  | Development | extra-muros | Task #302493 |  | 8.5 | 1.1.16
4615500% | Clara Bécares Rodríguez | Natura2000 | Analysis | Development | extra-muros | Task #302531: Data model revision and adaptation |  | 3.5 | 1.1.16
4615500% | Clara Bécares Rodríguez | Natura2000 |  | Development | extra-muros | Task #302493 |  | 1 | 1.1.16
4615500% | Clara Bécares Rodríguez | Natura2000 | Testing | Development | extra-muros | Task #303483: Testing activitites |  | 1 | 1.1.16
4615500% | Clara Bécares Rodríguez | Natura2000 | Analysis | Development | extra-muros | Task #302531: Data model revision and adaptation |  | 1 | 1.1.16
4615500% | Clara Bécares Rodríguez | Natura2000 | Meetings | Development | extra-muros | Task #302497: Biweekly meetings |  | 2 | 1.1.16
4615500% | Josu Olaso | Natura2000 | Testing | Development | extra-muros | Task #303483: Testing activitites |  | 5.5 | 1.1.16
4615500% | Natalia Orio Moreno | Natura2000 | Meetings | Development | extra-muros | Task #302497: Biweekly meetings |  | 2 | 1.1.16
4615500% | Oscar Esparza García | Natura 2000 backbone |  | Development | extra-muros | Task #303032: Review spatial changes of the submission 2025 | Review spatial changes of the submission 2025 | 3 | 1.2.135
4615400% | Alba Lallana Martín | Natura2000 |  | Development | extra-muros | Task #302493 |  | 8.5 | 1.1.16
4615400% | Clara Bécares Rodríguez | Natura2000 |  | Development | extra-muros | Task #302493 |  | 1.5 | 1.1.16
4615400% | Clara Bécares Rodríguez | Natura2000 | Maintenance | Development | extra-muros | Task #302527: Review and removal of deprecated services |  | 1 | 1.1.16
4615400% | Esther Ruiz | Natura 2000 backbone |  | Development | extra-muros | Task #303033: Review Lineage and critical changes | Review specific cases | 4 | 1.2.135
4615400% | Natalia Orio Moreno | Natura2000 | Meetings | Development | extra-muros | Task #302497: Biweekly meetings | prepartion of progress meeting | 2 | 1.1.16
4615400% | Oscar Esparza García | Natura 2000 backbone |  | Development | extra-muros | Task #303032: Review spatial changes of the submission 2025 | Review multipolygon changes of submission 2025 | 4 | 1.2.135
4615300% | Alba Lallana Martín | Natura2000 |  | Development | extra-muros | Task #302493 |  | 8.5 | 1.1.16
4615300% | Arkaitz Lasheras Sustacha | Natura 2000 backbone |  | Development | extra-muros | Task #303353: Columns | Delivered | 7 | 1.2.135
4615300% | Esther Ruiz | Natura 2000 backbone |  | Meeting | extra-muros | Task #302389: Meetings with DG-ENV, ETC and EEA | UL meeting | 2 | 1.2.135
4615300% | Natalia Orio Moreno | Natura2000 | Analysis | Development | extra-muros | Task #302531: Data model revision and adaptation | datamodel review | 2 | 1.1.16
4615300% | Oscar Esparza García | Natura 2000 backbone |  | Development | extra-muros | Task #303299: Provide change report by submission | Geometries for change report by submission | 3.5 | 1.2.135
4615000% | Alba Lallana Martín | Natura2000 |  | Development | extra-muros | Task #302496 |  | 2 | 1.1.16
4615000% | Alba Lallana Martín | Natura2000 |  | Development | extra-muros | Task #302493 |  | 5 | 1.1.16
4615000% | Arkaitz Lasheras Sustacha | Natura 2000 backbone |  | Development | extra-muros | Task #303020: Performing a full harvest of all countries in staging for an initial extraction |  | 1 | 1.2.135
4615000% | Clara Bécares Rodríguez | Natura2000 |  | Development | extra-muros | Task #302496 |  | 2 | 1.1.16
4614900% | Alba Lallana Martín | Natura2000 |  | Development | extra-muros | Task #302493 |  | 8.5 | 1.1.16
4614900% | Arkaitz Lasheras Sustacha | Natura 2000 backbone |  | Development | extra-muros | Task #303428: Ad-hoc extraction: Generate extraction of the species that are shown several times | Delivered | 8.5 | 1.2.135
4614900% | Esther Ruiz | Natura 2000 backbone |  | Development | extra-muros | Task #302627 | Extraction provided | 8 | 1.2.135
4614900% | Esther Ruiz | Natura 2000 backbone |  | Development | extra-muros | Task #302817: Ad-hoc extraction coordinates | Analysis and coordinations | 2 | 1.2.135
4614800% | Alba Lallana Martín | Natura2000 |  | Development | extra-muros | Task #302493 |  | 8.5 | 1.1.16
4614800% | Arkaitz Lasheras Sustacha | Natura 2000 backbone |  | Development | extra-muros | Task #303020: Performing a full harvest of all countries in staging for an initial extraction | Requiered for clean data | 8.5 | 1.2.135
4614800% | Esther Ruiz | Natura 2000 backbone |  | Meeting | extra-muros | Task #302389: Meetings with DG-ENV, ETC and EEA | Biweekly meeting: preparation and attendance | 4 | 1.2.135
4614800% | Esther Ruiz | Natura 2000 backbone |  | Development | extra-muros | Task #303033: Review Lineage and critical changes | Review specific cases | 4 | 1.2.135
4614700% | Alba Lallana Martín | Natura2000 |  | Development | extra-muros | Task #302493 |  | 8.5 | 1.1.16
4614700% | Arkaitz Lasheras Sustacha | Natura 2000 backbone |  | Development | extra-muros | Task #303832: AD hoc extraction: list of sites where an habitat has been reported more than once | Delivered | 8.5 | 1.2.135
4614700% | Clara Bécares Rodríguez | Natura2000 | Analysis | Development | extra-muros | Task #302531: Data model revision and adaptation |  | 4 | 1.1.16
4614700% | Oscar Esparza García | Natura 2000 backbone |  | Development | extra-muros | Task #302714: Detection of non changed polygons | improve geometry chnages calculation | 5 | 1.2.135
4614600% | Alba Lallana Martín | Natura2000 |  | Development | extra-muros | Task #302493 |  | 8.5 | 1.1.16
4614600% | Arkaitz Lasheras Sustacha | Natura 2000 backbone |  | Development | extra-muros | Task #303352: Sites added/deleted by lineage , bioregions and site type | Delivered | 8.5 | 1.2.135
4614600% | Clara Bécares Rodríguez | Natura2000 | Analysis | Development | extra-muros | Task #302531: Data model revision and adaptation |  | 2.5 | 1.1.16
4614600% | Esther Ruiz | Natura 2000 backbone |  | Meeting | extra-muros | Task #302389: Meetings with DG-ENV, ETC and EEA | UL meeting | 2 | 1.2.135
4614600% | Esther Ruiz | Natura 2000 backbone |  | Development | extra-muros | Task #303124: Possible issue with the comments | Testing and communication | 2 | 1.2.135
4614600% | Oscar Esparza García | Natura 2000 backbone |  | Development | extra-muros | Task #302714: Detection of non changed polygons | Review non-changed geometry calculation | 3.5 | 1.2.135

## pivot
| Values |  |  | Values |  |  | Values |  | Sum of Hours | Column Labels |  |  |  | Sum of Hours | Column Labels
Row Labels | Sum of Hours | Days | Row Labels | Sum of Hours | Sum of Hours2 | Row Labels | Sum of Hours | Days | Row Labels | (blank) | 1.1.16 | 1.2.135 | Grand Total | Row Labels | (blank) | 1.1.16 | 1.2.135 | Grand Total
(blank) |  | 0% | 1.1.16 | 256 | 69.19% | Task #302493 | 115.5 | 14.4375 | Alba Lallana Martín |  | 141 |  | 141 | extra-muros |  | 256 | 114 | 370
(blank) |  | 0% | 1.2.135 | 114 | 30.81% | Task #303483: Testing activitites | 53 | 6.625 | Arkaitz Lasheras Sustacha |  |  | 42 | 42 | (blank)
(blank) |  | 0% | (blank) |  | 0% | Task #302531: Data model revision and adaptation | 32.5 | 4.0625 | Clara Bécares Rodríguez |  | 64 |  | 64 | Grand Total |  | 256 | 114 | 370
Natura2000 | 256 | 69.19% | Grand Total | 370 | 100% | Task #303484: Bug fixing | 26 | 3.25 | Esther Ruiz |  |  | 50 | 50
(blank) | 131.5 | 35.54% |  |  |  | Task #303352: Sites added/deleted by lineage , bioregions and site type | 16.5 | 2.0625 | Isabel Olea |  | 8 |  | 8
1.1.16 | 131.5 | 35.54% |  |  |  | Task #302389: Meetings with DG-ENV, ETC and EEA | 16 | 2 | Josu Olaso |  | 15 |  | 15
Testing | 53 | 14.32% |  |  |  | Task #303332 | 12 | 1.5 | Natalia Orio Moreno |  | 27 |  | 27
1.1.16 | 53 | 14.32% |  |  |  | Task #303033: Review Lineage and critical changes | 11 | 1.375 | Oscar Esparza García |  |  | 22 | 22 | Sum of Hours | Column Labels
Analysis | 32.5 | 8.784% |  |  |  | Task #303428: Ad-hoc extraction: Generate extraction of the species that are shown several times | 10.5 | 1.3125 | Yolanda Carrasco |  | 1 |  | 1 | Row Labels | (blank) | 4617100% | 4617000% | 4616900% | 4616800% | 4616700% | 4616400% | 4616300% | 4616200% | 4616100% | 4616000% | 4615700% | 4615600% | 4615500% | 4615400% | 4615300% | 4615000% | 4614900% | 4614800% | 4614700% | 4614600% | Grand Total
1.1.16 | 32.5 | 8.784% |  |  |  | Task #303832: AD hoc extraction: list of sites where an habitat has been reported more than once | 10.5 | 1.3125 | (blank) |  |  |  |  | Alba Lallana Martín |  |  |  | 2 | 8.5 | 8.5 | 7 | 7.5 | 8.5 | 8.5 | 8.5 | 7 | 8.5 | 8.5 | 8.5 | 8.5 | 7 | 8.5 | 8.5 | 8.5 | 8.5 | 141
Maintenance | 3 | 0.8108% |  |  |  | Task #302497: Biweekly meetings | 10 | 1.25 | Grand Total |  | 256 | 114 | 370 | Arkaitz Lasheras Sustacha | [15 empty] | 7 | 1 | 8.5 | 8.5 | 8.5 | 8.5 | 42
1.1.16 | 3 | 0.8108% |  |  |  | Task #303020: Performing a full harvest of all countries in staging for an initial extraction | 9.5 | 1.1875 | [5 empty] | Clara Bécares Rodríguez |  | 10.5 | 4 | 6 | 6.5 | 5.5 |  | 4.5 | 3.5 |  |  | 1 | 3 | 8.5 | 2.5 |  | 2 |  |  | 4 | 2.5 | 64
Meetings | 10 | 2.703% |  |  |  | Task #302714: Detection of non changed polygons | 8.5 | 1.0625 | [5 empty] | Esther Ruiz | [5 empty] | 2 | 2 | 4 | 4 | 6 |  |  | 4 |  | 4 | 2 |  | 10 | 8 |  | 4 | 50
1.1.16 | 10 | 2.703% |  |  |  | Task #302627 | 8 | 1 | [5 empty] | Isabel Olea |  | 2 | 2 | 2 | 2 | [16 empty] | 8
Bug fixing | 26 | 7.027% |  |  |  | Task #303353: Columns | 7 | 0.875 | [5 empty] | Josu Olaso | [11 empty] | 4 | 5.5 | 5.5 | [7 empty] | 15
1.1.16 | 26 | 7.027% |  |  |  | Task #303032: Review spatial changes of the submission 2025 | 7 | 0.875 | [5 empty] | Natalia Orio Moreno |  | 3 | 5 | 2 | 4 |  | 2 |  |  | 3 |  |  | 2 | 2 | 2 | 2 | [5 empty] | 27
Natura 2000 backbone | 114 | 30.81% |  |  |  | Task #302496 | 4 | 0.5 | [5 empty] | Oscar Esparza García | [9 empty] | 3 |  |  |  | 3 | 4 | 3.5 |  |  |  | 5 | 3.5 | 22
(blank) | 114 | 30.81% |  |  |  | Task #303299: Provide change report by submission | 3.5 | 0.4375 | [5 empty] | Yolanda Carrasco |  |  |  | 1 | [17 empty] | 1
1.2.135 | 114 | 30.81% |  |  |  | Task #302527: Review and removal of deprecated services | 3 | 0.375 | [5 empty] | (blank)
Grand Total | 370 | 100% |  |  |  | Task #303124: Possible issue with the comments | 2 | 0.25 | [5 empty] | Grand Total |  | 15.5 | 11 | 13 | 21 | 16 | 11 | 16 | 16 | 20.5 | 8.5 | 12 | 23 | 27.5 | 21 | 23 | 10 | 27 | 25 | 26 | 27 | 370
[6 empty] | Task #302817: Ad-hoc extraction coordinates | 2 | 0.25
[6 empty] | Task #304183 | 2 | 0.25
[6 empty] | (blank) |  | 0
[6 empty] | Grand Total | 370 | 46.25

## split
1.1.16 | 256 | 69.19%
1.2.135 | 114 | 30.81%
(blank) |  | 0%
Grand Total | 370 | 100%

## CODES
Rollup | 2025 MPS | 2025 Level 3 label | Consultant
1.1.0 | 1.1.20 | Annual datasets of National Emission Reduction Committments Directive (NECD) | Tracasa
1.1.0 | 1.1.21 | Annual datasets of Long-range Transboundary Air Pollution Convention | Tracasa
1.1.0 | 1.1.23 | Annual datasets: Mercury, Energy Community LCPs | Tracasa
1.1.0 | 1.1.25 | Data reporting for Seveso establishments under the Seveso Directive | Tracasa
1.1.0 | 1.1.29 | Noise - Data Reporting | Tracasa
1.1.0 | 1.1.30 | Air - Annual Datasets of Ambient Air Quality Directive Reporting | Tracasa
1.1.0 | 1.1.31 | Air - Switch to Reportnet 3 for air quality dataflows | Tracasa
1.1.0 | 1.1.35 | Bathing Water - Dataflows and database update | Tracasa
1.1.0 | 1.1.40 | UWWTD - dataflow and database update | Tracasa
1.1.0 | 1.1.43 | WISE SoE and watch list - dataflow and database update | Tracasa
1.1.0 | 1.2.2 | EUNIS database and species taxonomic backbone (not AWP) | Tracasa
1.1.0 | 1.2.20 | Industrial Emissions Portal Website | Tracasa
1.1.0 | 1.2.23 | Data viewer: Policies and Measures - NECD | Tracasa
1.1.0 | 1.2.25 | Health - European Environment and Health Atlas | Tracasa
1.1.0 | 1.2.26 | Air - European Air Quality City Ranking | Tracasa
1.1.0 | 1.2.27 | Air - European Air Quality Index and App | Tracasa
1.1.0 | 1.2.29 | Air - Air Quality Up-to-Date Data Viewer Maintenance | Tracasa
1.1.0 | 1.2.30 | Air - AQ Data Tables | Tracasa
1.1.0 | 1.2.32 | Air - AQ Maps | Tracasa
1.1.0 | 1.2.33 | Noise - Data Viewers, Data Products | Tracasa
1.1.0 | 1.2.35 | Health - Viewer on combined health impacts from road noise and air pollution | Tracasa
1.1.0 | 1.2.37 | Bathing Water Directive - data, dashboards and map products | Tracasa
1.1.0 | 1.2.42 | UWWTD - data, dashboards, and country profiles | Tracasa
1.1.0 | 1.2.46 | WISE SoE and watch list - data, dashboards and map products | Tracasa
1.1.0 | 1.3.22 | Air Pollution 2024 | Tracasa
1.1.0 | 1.3.27 | Harm to human health from air pollution in Europe: burden of disease status, 2025 | Tracasa
1.1.0 | 1.3.28 | Europe's air quality status 2025 | Tracasa
1.1.0 | 1.3.39 | Exceedance of air quality standards in Europe | Tracasa
1.1.0 | 1.3.42 | Premature deaths due to exposure to fine particulate matter in Europe | Tracasa
2.1.0 | 2.1.10 | Data reporting under the Governance Regulation - mitigation and energy | Tracasa
2.1.0 | 2.1.11 | Data reporting under the Governance Regulation - adaptation | Tracasa
2.1.0 | 2.1.20 | Annual EU greenhouse gas inventory 1990-2023 Common Reporting Tables | Tracasa
2.1.0 | 2.1.4 | Data reporting under the Fuel Quality Directive | Tracasa
2.1.0 | 2.1.5 | Data reporting on passenger cars | Tracasa
2.1.0 | 2.1.6 | Data reporting on light-duty vehicles (vans) | Tracasa
2.1.0 | 2.1.7 | Data reporting on heavy-duty vehicles | Tracasa
2.1.0 | 2.1.8 | Data reporting on real world emissions | Tracasa
2.1.0 | 2.3.74 | Summer Product (not AWP) | Tracasa
3.1.0 | 3.1.21 | Dataset of Reuse of Products | Tracasa
3.1.0 | 3.1.22 | Dataset of Sewage Sludge | Tracasa
4.1.6 | 4.1.6 | Innovation - AI Large Language Models exercises | Tracasa
4.1.6 | 4.1.7 | Innovation - Data AI (Machine and Deep learning) | Tracasa
4.3.1 | 4.3.1 | Workspace-Common Workspace (CWS) | Tracasa
4.3.1 | 4.3.6 | Platform-Data Automation Services (ETL,FME) | Tracasa
4.3.1 | 4.3.9 | Platform-Geospatial (ArcGis & Web Services) | Tracasa
4.4.5 | 4.4.5 | Information management | Tracasa
1.1.0 | 1.1.22 | Annual datasets of Industrial Emission Portal Regulation and related EU law | Bilbomatica
1.1.0 | 1.1.30 | Air - Annual Datasets of Ambient Air Quality Directive Reporting | Bilbomatica
1.1.0 | 1.1.31 | Air - Switch to Reportnet 3 for air quality dataflows | Bilbomatica
1.1.0 | 1.1.46 | Habitats Directive Art. 17, Birds Directive Art. 12 dataflows and Resolution 8 of Bern Convention | Bilbomatica
1.1.0 | 1.1.48 | Natura 2000 dataflow, Bern Convention's Emerald dataflows, Sufficiency assessments and review semina | Bilbomatica
1.1.0 | 1.1.49 | Invasive Alien Species (IAS) EU Regulation 1143/2014 dataflow | Bilbomatica
1.1.0 | 1.1.50 | National Restoration Plans (not AWP) | Bilbomatica
1.2.0 | 1.2.61 | Natura 2000 data tools and map viewers (incl Emerald support), Derogation dashboards | Bilbomatica
2.1.0 | 2.1.1 | Data reporting on Ozone depleting substances and F-gases | Bilbomatica
4.4.5 | 4.1.5 | Datahub & Datahub Lab | Bilbomatica
4.4.5 | 4.3.25 | App-Data dissemination | Bilbomatica
4.4.5 | 4.4.5 | Information management | Bilbomatica

## Codes to MPS
Project | Category | MPS code
Air Quality | AD HOC product | 1.1.0
Air Quality | Monitoring & QC | 1.1.0
Air Quality | Meetings and coordination of activities | 1.1.0
Air Quality | Development - Backend | 1.1.0
Air Quality | ETL | 1.1.0
Air Quality | Development - Infrastucture | 1.1.0
Air Quality | Development - Frontend | 1.1.0
Air Quality | BI dashboarding | 1.1.0
Air Quality | Air Quality | 1.1.0
Mobile Air Quality Index App | Development - Frontend | 1.1.0
CWS support | Generic case | 4.3.1
CWS support | Permissions | 4.3.1
CWS support | ArcGis | 4.3.1
Data visualization support | Tableau visualization | x
DataHub | DataHub | 4.4.5
Datasets for SDI | SDI Registration 4. Finalisation | x
Datasets for SDI | SDI Registration 5. Publication | x
DiscoMap | WebAppbuilder WAB | 4.3.9
DiscoMap | Monitoring - Statistics | 4.3.9
DiscoMap | Discomap Tools | 4.3.9
DiscoMap | Clean up | 4.3.9
DiscoMap | Migration towards enterprise | 4.3.9
DiscoMap | Infrastructure | 4.3.9
DiscoMap | Maintenance - Migration - Upgrade | 4.3.9
DiscoMap | Development | 4.3.9
DiscoMap | GIS administration 2023 | 4.3.9
DiscoMap | Automation & Scripting | 4.3.9
DiscoMap | Products - IDP | 4.3.9
DiscoMap | ArcGIS Server | 4.3.9
DiscoMap | Experience Builder | 4.3.9
DiscoMap | Wiki-Documentation | 4.3.9
DiscoMap | Discomaperies (not specific) | 4.3.9
DiscoMap | APIs & Integrations | 4.3.9
DiscoMap | Public things | 4.3.9
DiscoMap | Discomap 3 | 4.3.9
DiscoMap | Hub | 4.3.9
DiscoMap Helpdesk | Apps, viewers and Templates | 4.3.9
DiscoMap Helpdesk | ArcGIS Portal | 4.3.9
DiscoMap Helpdesk | Maintenance and cleaning | 4.3.9
DiscoMap Helpdesk | WebAppBuilder | 4.3.9
DiscoMap Helpdesk | N2K | 4.3.9
DiscoMap Helpdesk | Copernicus | 4.3.9
DiscoMap Helpdesk | Infrastructure (where we need helpdesk help) | 4.3.9
DiscoMap Helpdesk | EEA public content | 4.3.9
DiscoMap Helpdesk | Other Applications | 4.3.9
DiscoMap Helpdesk | FME | 4.3.6
DiscoMap Helpdesk | ArcGIS Enterprise | 4.3.9
DiscoMap Helpdesk | ArcGIS Pro | 4.3.9
DiscoMap Helpdesk | Linked to security | 4.3.9
DiscoMap Helpdesk | ExperienceBuilder | 4.3.9
DiscoMap Helpdesk | Monitor | 4.3.9
DiscoMap Helpdesk | Data | 4.3.9
DiscoMap Helpdesk | User Management | 4.3.9
DiscoMap Helpdesk | Licenses | 4.3.9
DiscoMap Helpdesk | ArcGIS Servers & Services | 4.3.9
DiscoMap Helpdesk | User support | 4.3.9
EUNIS2 database | EUNIS2 database | 1.1.0
EUNIS2 database | Project Management | 1.1.0
EyeOnEarth | FME Development | 1.1.0 | MLW
EyeOnEarth | Web development | 1.1.0 | MLW
EyeOnEarth | EyeOnEarth | 1.1.0 | MLW
GIS Library | NEC+LRTAP | X
GIS Library | FME support | 4.3.6
GIS Library | Eurostat FME Package | 4.3.6
GIS Library | FME Infraestructure | 4.3.6
GIS Library | Noise | 1.1.0
GIS Library | DISCODATA | x
GIS Library | Data integration | x
GIS Library | ACC Support | x
GIS Library | Applications | x
GIS Library | Range Tool | x
GIS Library | BISE | 1.1.0
GIS Library | Tracasa 2024 planning meeting | x
GIS Library | Security | x
GIS Library | Tableau Consultancy | x
GIS Library | ETS | x
GIS Library | Discomap | 4.3.9
GIS Library | GHG | X
GIS Library | Industrial emissions | 1.1.0
GIS Library | AI integration | 4.1.6
GIS Library | CDDA | 1.1.0
JEDI (Join Environmental Data Infrastructure) | JEDI (Join Environmental Data Infrastructure) | 4.4.5
Natura2000 | Tableau dashboards | 1.1.0
Natura2000 | .Net for the N2K app | 1.1.0
Natura2000 | .Net for the N2K app | 1.1.0
Natura2000 | .Net for the Emerald app | 1.1.0
Natura2000 | Experience Builder viewer | 1.1.0
Natura2000 | PM & Meetings | 1.1.0
Natura2000 | WAP for Emerald | 1.1.0
Natura2000 | GIS analysis and geoprocesses | 1.1.0
Natura2000 | Data processing (FME&SQL) for N2K | 1.1.0
Natura2000 | Data processing (FME&SQL) for Emerald | 1.1.0
Natura2000 | Natura2000 | 1.1.0
Natura 2000 backbone | Natura 2000 backbone | 1.1.0
Reportnet dataflows | Dataflows - Noise | 1.1.0
Reportnet dataflows | Dataflows - GovReg PaMs | 2.1.0
Reportnet dataflows | Dataflows - GovReg | 2.1.0
Reportnet dataflows | Dataflows - UWWTD | 1.1.0
Reportnet dataflows | Dataflows - GovReg Projections | 2.1.0
Reportnet dataflows | Dataflows - GovReg Adaptation | 2.1.0
Reportnet dataflows | Dataflows - _Process improvements | 4.4.5
Reportnet dataflows | Dataflows - ODS | 2.1.0
Reportnet dataflows | Dataflows - F-gases | 2.1.0
Reportnet dataflows | Dataflows - Inventories | 2.1.0
Reportnet dataflows | Dataflows - Nitrates | 1.1.0
Reportnet dataflows | Dataflows - DWD | 1.1.0
Reportnet dataflows | Dataflows - Other/generic | x
Reportnet dataflows | Dataflows - Habides | 1.1.0 | Tracasa - use 6.4.2
Reportnet dataflows | Dataflows - Nature pledges | 1.1.0
Reportnet dataflows | Dataflows - Invasive Alien Species | 1.1.0
Reportnet dataflows | Dataflows - Derogations | 1.1.0
Reportnet dataflows | Dataflows - IED EU Registry | 1.1.0
Reportnet dataflows | Dataflows - AQ e-Reporting | 1.1.0
Reportnet dataflows | Dataflows - Nature reporting | 1.1.0
Reportnet dataflows | Dataflows - NECD+LRTAP | 1.1.0
Reportnet dataflows | Dataflows - NEC-PAMs | 2.1.0
Reportnet dataflows | Dataflows - GovReg Auctioning Revenues | 2.1.0
Reportnet dataflows | Dataflows - Waste | 3.1.0
Reportnet dataflows | Dataflows - E-PRTR and LCP | 1.1.0
Reportnet dataflows | Dataflows - E-PRTR | 1.1.0
Reportnet dataflows | Specific agreement management | 4.4.5
Reportnet dataflows | Dataflows - GovReg support to developing countries | 2.1.0
Reportnet dataflows | Dataflows - Sludge | 3.1.0
Reportnet dataflows | Dataflows - N2K/Emerald SDF DEM | 1.1.0
Reportnet dataflows | Dataflows - Seveso establishments | 1.1.0
Reportnet dataflows | Dataflows - Seveso accidents | 1.1.0
Reportnet dataflows | Dataflows - HDV | 2.1.0
Reportnet dataflows | Dataflows - Fuel quality | 2.1.0
Reportnet dataflows | Dataflows - WISE SoE | 1.1.0
Reportnet dataflows | Dataflows - NECPR | 1.1.0
Reportnet dataflows | Dataflows - NRR | 1.1.0
Reportnet 3 | Reportnet 3 | 4.4.5
Summer is coming | Summer is coming | 2.1.0
UWWTD | UWWTD | 1.1.0
WISE | Data Reporting | 1.1.0
WISE | Testing | 1.1.0
WISE | Documentation | 1.1.0
WISE | ORG | 1.1.0
WISE | Development | 1.1.0
WISE | Data Products | 1.1.0
WISE | Data Extracts | 1.1.0
WISE | Helpdesk | 1.1.0
WISE | Data Visualisation | 1.1.0
WISE Marine | Data preparation for Data products | 1.1.0 | Charged to core when no ENV contract
WISE SoW | Dashboards | 1.1.0
WISE SoW | Database | 1.1.0
WISE SoW | Services | 1.1.0
WISE SoW | Statistics | 1.1.0
WISE SoW | ORG | 1.1.0